## _Doc Rule
| 문서 번호 | CostType
0 | None | None
1 | Status | Cash
2 | Boss | Coin
3 | _
4 | Upgrade
5 | Weapon
6 | Shop
7 | StartStatus
8 | String
9 | Path

## _Feature List
스탯 | 전투 | 강화 | 제작 | 상점 | 데이터
공격력 | 몬스터 생성 | 공격력 | 생성 | 광고 제거 | TableParser
체력 |  | 체력 | 조합 | 자동 제작 | Web
방어력 |  | 방어력 | 인벤토리 잠금 해제
제작 속도

## _Schedule
열 너비 6 | 행 높이 16.5 | 시작일 | 2022-06-09 | [9 empty] | 시작 예정 |  | 1 |  | 진행 |  | 2 |  | 완료 |  | 3 |  | 목표 |  | 4
2022-06-12 20:56 |  |  |  | 6
기능 | 시작 | 목표 | 완료 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
프레임워크 | 6/9 | 6/10 | 6/10 | 6 9: 1; 6 10: 3; 6 11: 4
몬스터 |  |  |  | 6 16: 4
캐릭터 스탯 | 6/14 | 6/14 | 6/14 | 6 14: 1; 6 15: 4
인게임 UML |  |  |  | 6 14: 4
Excel To Csv Auto | 6/12 | 6/12 | 6/12 | 6 12: 3
테이블 연동 | 6/12 | 6/12 | 6/12 | 6 12: 1; 6 15: 4
게임 매니저 | 6/14 | 6/14 | 6/14 | 6 14: 1; 6 17: 4
테이블 | 6/10 | 6/12 | 6/12 | 6 10: 1; 6 11: 2; 6 12: 1; 6 19: 4
테이블 파서 | 6/10 | 6/11 | 6/11 | 6 10: 1; 6 11: 2; 6 12: 4
UI 디자인 | 6/10 | 6/10 | 6/10 | 6 10: 2; 6 11: 4
상점
업그레이드
제작
전투
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL

## Status
ID | Level | MaxInventory
110001 | 1 | 4

## Monster
ID | MonsterType | IconID | Health | AttackPower | DefencePower
200001 | Boss | 930001 | 100 | 10 | 5
200002 | Boss | 930002 | 150 | 20 | 10
200003 | Boss | 930003 | 200 | 30 | 15
200004 | Boss | 930002 | 300 | 40 | 20
200005 | Boss | 930003 | 350 | 50 | 25
200006 | Boss | 930001 | 400 | 60 | 30
201001 | Unknown | 930001 | 10 | 5 | 1

## Upgrade
ID | UpgradeType | IconID | Price | IncreaseStat
401001 | Weapon | 940001 | 5000 | 5
401002 | Defence | 940002 | 10000 | 1
401003 | Health | 940003 | 2500 | 10

## Craft
ID | IconID | IconBorderID | Level | AttackPower
510000 | 0 | 950001 | 0 | 0
510001 | 910001 | 950002 | 1 | 5
510002 | 910002 | 950002 | 2 | 10
510003 | 910003 | 950002 | 3 | 20
510004 | 910004 | 950002 | 4 | 40
510005 | 910005 | 950002 | 5 | 80
510006 | 910006 | 950002 | 6 | 160

## Shop
ID | IconID | CostType | EngPrice | KorPrice | RewardType | Reward
610001 | 910007 | Cash | 399 | 4900 | Ads | 0
610002 | 920001 | Ads | 0 | 0 | Coin | 1000

## StartStatus
ID | InventorySlot | Gold | AtkPower | DefPower | Health
710001 | 4 | 1000 | 50 | 2 | 100

## String
ID | Eng | Kor
810001 | Touch To Play | 터치하여 시작
810002 | Start Game | 게임 시작
810003 | Boss | 보스
810004 | Upgrade | 강화
810005 | Craft | 제작
810006 | Shop | 상점
810007 | Ad Remove | 광고 제거

## Path
ID | AssetType | Path
910001 | Sprite | Art/Sprite/Weapon/Sword
910002 | Sprite | Art/Sprite/Weapon/Bow
910003 | Sprite | Art/Sprite/WeaponAxe
910004 | Sprite | Art/Sprite/Weapon/Hammer
910005 | Sprite | Art/Sprite/Weapon/HDualBlade
910006 | Sprite | Art/Sprite/Weapon/BattleAxe
920001 | Sprite | Art/Sprite/Shop/AdRemove
930001 | Sprite | Art/Sprite/Boss/Boss0
930002 | Sprite | Art/Sprite/Boss/Boss1
930003 | Sprite | Art/Sprite/Boss/Boss2
940001 | Sprite | Art/Sprite/Upgrade/AttackPower
940002 | Sprite | Art/Sprite/Upgrade/DeffencePower
940003 | Sprite | Art/Sprite/Upgrade/HealthUp
950001 | Sprite | Art/Sprite/Craft/DisableBorder
950002 | Sprite | Art/Sprite/Craft/EnableBorder