## _Doc Rule
| 문서 번호 | CostType
0 | None | None
1 | Status | Cash
2 | Boss | Coin
3 | _
4 | Upgrade
5 | Weapon
6 | Shop
7 | StartStatus
8 | String
9 | Path

## _Feature List
스탯 | 전투 | 강화 | 제작 | 상점 | 데이터
공격력 | 몬스터 생성 | 공격력 | 생성 | 광고 제거 | TableParser
체력 |  | 체력 | 조합 | 자동 제작 | Web
방어력 |  | 방어력 | 인벤토리 잠금 해제
제작 속도

## _Schedule
열 너비 6 | 행 높이 16.5 | [11 empty] | 시작 |  | 1 |  | 진행 |  | 2 |  | 목표 |  | 3 |  | 완료 |  | 4
2022-06-18 00:02 |  |  |  | 6
기능 | 시작 | 목표 | 완료 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
프레임워크 | 6/9 | 6/10 | 6/11 | 6 9: 1; 6 10: 3; 6 11: 4
몬스터 | 6/16 | 6/18 | 6/18 | 6 16: 1; 6 18: 3
캐릭터 스탯 | 6/14 | 6/14 | 6/15 | 6 14: 1; 6 15: 4
인게임 UML | 6/13 | 6/13 | 6/14 | 6 13: 1; 6 14: 4
Excel To Csv Auto | 6/12 | 6/12 | 6/12 | 6 12: 4
테이블 연동(상점 제외) | 6/13 | 6/13 | 6/13 | 6 13: 4; 6 14: 2
테이블 | 6/10 | 6/19 | 6/19 | 6 10: 1; 6 11: 2; 6 12: 2; 6 14: 2; 6 17: 2; 6 19: 3
테이블 파서 | 6/10 | 6/11 | 6/12 | 6 10: 1; 6 11: 2; 6 12: 4
UI 디자인 | 6/10 | 6/10 | 6/11 | 6 10: 1; 6 11: 4
상점
업그레이드 | 6/15 | 6/15 | 6/15 | 6 15: 4
제작
전투 | 6/16 | 6/18 | 6/18 | 6 16: 1; 6 17: 2; 6 18: 3
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL
NULL

## Monster
ID | MonsterType | IconID | Health | AttackPower | DefencePower
200001 | Boss | 930001 | 100 | 10 | 5
200002 | Boss | 930002 | 150 | 20 | 10
200003 | Boss | 930003 | 200 | 30 | 15
200004 | Boss | 930002 | 300 | 40 | 20
200005 | Boss | 930003 | 350 | 50 | 25
200006 | Boss | 930001 | 400 | 60 | 30
201001 | Unknown | 930001 | 10 | 5 | 1

## Upgrade
ID | UpgradeType | Level | IconID | Price | IncreaseStat
401000 | Attack | 0 | 940001 | 5000 | 5
401001 | Attack | 1 | 940001 | 6000 | 5
402000 | Defence | 0 | 940002 | 10000 | 1
402001 | Defence | 1 | 940002 | 11000 | 1
403000 | Health | 0 | 940003 | 2500 | 10
403001 | Health | 1 | 940003 | 3000 | 10

## Item
ID | ItemType | IconID | Lock | IconBorderID | Level | AttackPower
500000 | None | 0 | TRUE | 950001 | 0 | 0
500001 | None | 0 | FALSE | 950002 | 0 | 0
510001 | Weapon | 910001 | FALSE | 950002 | 1 | 5
510002 | Weapon | 910002 | FALSE | 950002 | 2 | 10
510003 | Weapon | 910003 | FALSE | 950002 | 3 | 20
510004 | Weapon | 910004 | FALSE | 950002 | 4 | 40
510005 | Weapon | 910005 | FALSE | 950002 | 5 | 80
510006 | Weapon | 910006 | FALSE | 950002 | 6 | 160

## Shop
ID | IconID | CostType | EngPrice | KorPrice | RewardType | Reward
610001 | 910007 | Cash | 399 | 4900 | Ads | 0
610002 | 920001 | Ads | 0 | 0 | Coin | 1000

## StartStatus
ID | Level | InventorySlot | AddCoin | AtkPower | DefPower | Health | CraftLevel | AtkDelay | AtkSpeed
710000 | 0 | 4 | 5 | 50 | 2 | 100 | 1 | 0.2 | 0.5
710001 | 1 | 5 | 10 | 55 | 4 | 150 | 2 | 0.2 | 0.5
710002 | 2 | 6 | 15 | 60 | 6 | 200 | 3 | 0.2 | 0.5
710003 | 3 | 7 | 20 | 65 | 8 | 250 | 4 | 0.2 | 0.5
710004 | 4 | 8 | 25 | 70 | 10 | 300 | 5 | 0.2 | 0.5
710005 | 5 | 9 | 30 | 75 | 12 | 350 | 6 | 0.2 | 0.5
710006 | 6 | 10 | 35 | 80 | 14 | 400 | 7 | 0.2 | 0.5
710007 | 7 | 11 | 40 | 85 | 16 | 450 | 8 | 0.2 | 0.5
710008 | 8 | 12 | 45 | 90 | 18 | 500 | 9 | 0.2 | 0.5
710009 | 9 | 13 | 50 | 95 | 20 | 550 | 10 | 0.2 | 0.5
710010 | 10 | 14 | 55 | 100 | 22 | 600 | 11 | 0.2 | 0.5
710011 | 11 | 15 | 60 | 105 | 24 | 650 | 12 | 0.2 | 0.5
710012 | 12 | 16 | 65 | 110 | 26 | 700 | 13 | 0.2 | 0.5
710013 | 13 | 17 | 70 | 115 | 28 | 750 | 14 | 0.2 | 0.5
710014 | 14 | 18 | 75 | 120 | 30 | 800 | 15 | 0.2 | 0.5
710015 | 15 | 19 | 80 | 125 | 32 | 850 | 16 | 0.2 | 0.5
710016 | 16 | 20 | 85 | 130 | 34 | 900 | 17 | 0.2 | 0.5

## String
ID | Eng | Kor
810001 | Touch To Play | 터치하여 시작
810002 | Start Game | 게임 시작
810003 | Boss | 보스
810004 | Upgrade | 강화
810005 | Craft | 제작
810006 | Shop | 상점
810007 | Ad Remove | 광고 제거

## Path
ID | AssetType | Path
910001 | Sprite | Art/Sprite/Weapon/Sword
910002 | Sprite | Art/Sprite/Weapon/Bow
910003 | Sprite | Art/Sprite/WeaponAxe
910004 | Sprite | Art/Sprite/Weapon/Hammer
910005 | Sprite | Art/Sprite/Weapon/HDualBlade
910006 | Sprite | Art/Sprite/Weapon/BattleAxe
920001 | Sprite | Art/Sprite/Shop/AdRemove
930001 | Sprite | Art/Sprite/Boss/Boss0
930002 | Sprite | Art/Sprite/Boss/Boss1
930003 | Sprite | Art/Sprite/Boss/Boss2
940001 | Sprite | Art/Sprite/Upgrade/AttackPower
940002 | Sprite | Art/Sprite/Upgrade/DeffencePower
940003 | Sprite | Art/Sprite/Upgrade/HealthUp
950001 | Sprite | Art/Sprite/Craft/DisableBorder
950002 | Sprite | Art/Sprite/Craft/EnableBorder